**Grassroots Organizations Capacity Assessments (GOCA) – Chrey Community Leaarning Center**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **GOCA Summary Table in Chrey Commune** | | | | | | | | |
| **Category** | **Governance and Administration** | | **CLC Management** | **Financial Management** | **Community Investment Plan (CIP)** | **External Relations** | | **Total Average Score** |
| **Initial Score** | 0.30 | 0.00 | | 0.20 | 0.15 | 0.55 | **0.24** | |
| **Second Score** | 0.80 | 0.65 | | 0.60 | 1.00 | 0.80 | **0.77** | |
| **Third Score** | 2.85 | 1.85 | | 3.80 | 2.20 | 0.85 | **2.31** | |
| **Fourth Score** | 2.75 | 2.10 | | 3.95 | 2.60 | 2.40 | **2.76** | |
| **Fifth**  **Score** | 3.40 | 3.15 | | 3.65 | 2.80 | 1.50 | **2.90** | |

|  |
| --- |
| **Action Points (July 2017 –Nov 2017)** |
| **KEY ACTION POINT 1: Community Learning Centre Management**   |  |  |  | | --- | --- | --- | | **Specific Action Points** | **By whom** | **By when** | | CLCMCs to develop strategic plan | CLCMC members | July, 2017 | | CLCMCs to develop an annual operational plan and work Plan | CLCMC members | Aug, 2017 | | CLC Support Committee to meet on a monthly basis and develop a work plan based on Strategic Plan and Operational plan | CLCM members | July, 2017 | | CLCMC to operationalize Strategic Plan and Operational Plan | CLCMC members | Sept, 2017 |   **KEY ACTION POINT 2: Commune Investment Plan (CIP)**   |  |  |  | | --- | --- | --- | | **Specific Action Points** | **By whom** | **By when** | | CLCMC update CLC to commune council (CIP) | CLCMC members | Sept, 2017 |   **KEY ACTION POINT 3: External Relations and Resources Mobilization**   |  |  |  | | --- | --- | --- | | **Specific Action Points** | **By whom** | **By when** | | CLCMCs to provide reports to DoE every term | CLCMC members | July, 2017 | |

****

The project “Breaking the Cycle of Youth Marginalization and Poverty and Vulnerability in Rural Communities in Cambodia” is implemented by ACTED and KYA thanks to funding from the European Union.